## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group 4 — Digital Vanguard | Completed | 11
Project title | Nama Nameng: A Mobile and Web-Based Ordering, Payment and Queue Management System | In Progress | 0
Stakeholder or organisation | Nama Nameng (Chisa Nyama) — Owner: Doja | Not Started | 0
Group mentor | To be confirmed with module coordinator | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 18 Aug 2026 – 26 Aug 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Completed the project deliverables, including SRS, Microsoft Project Plan, Progress Tracker, Flutter and ASP.NET applications, backend configuration, testing, documentation and GitHub uploads. | Contribution entries | 5
Main challenge | Deciding the payment approach — full online payment was descoped to cash-on-collection after feasibility review, which required updating the requirements change log. | Verified entries | 5
Next planned activity | All planned project work is complete; retain final evidence and repository links for submission. | Unverified entries | 0
|  | Stakeholder engagements | 2
Phase 2 Snapshot | Group Response | Task Status | Count
Reporting phase | Unit 3 / Phase 2 | Completed | 12
Reporting period | 27 Aug 2026 – 23 Sep 2026 | In Progress | 0
Overall status | Completed | Not Started | 0
Overall % complete | 100% | Delayed | 0
Main achievement | Completed system architecture, Use Case Diagram, sequence diagrams, ERD, Flutter and ASP.NET interface prototypes, and Navigation Flow diagram. | Blocked | 0
Main challenge | Phase 2 deliverables completed and checked against project requirements. | Overdue | 0
Next planned activity | All Phase 2 deliverables completed.
|  | Contribution Summary | Count
|  | Contribution entries | 11
|  | Verified entries | 11
|  | Unverified entries | 0
|  | Stakeholder engagements | 1
Phase 3 Snapshot | Group Response | Task Status | Count
Reporting phase | Phase 3 | Completed | 18
Reporting period | 1 Oct 2026 – 30 Oct 2026 | In Progress | 0
Overall status | Completed | Not Started | 0
Overall % complete | 100% | Delayed | 0
Main achievement | Completed the Supabase backend, Flutter customer and staff/manager apps, ASP.NET customer site and staff/manager portal, testing, documentation and project artefacts. | Blocked | 0
Main challenge | Outstanding implementation, security, testing, stakeholder evaluation and documentation tasks have been completed. | Overdue | 0
Next planned activity | All planned project activities are complete; finalise submission using the completed repository and project files.
|  | Contribution Summary | Count
|  | Contribution entries | 6
|  | Verified entries | 6
|  | Unverified entries | 0
|  | Stakeholder engagements | 0

## GitHub Upload Plan
Simple GitHub Upload Plan
Purpose | Each assigned person uploads their allocated project file to the group GitHub repository. Neo contributed to both codebases but is not assigned a GitHub upload.
Member | What to upload | Suggested repository location / filename | Done? | GitHub link / notes
Lesedi | All Flutter code (customer + staff/manager apps and related Flutter files/tests) | flutter/ (complete Flutter project) | Yes | Completed; uploaded file is available in the group GitHub repository.
Hlayiseka | All ASP.NET code (customer web app + staff/manager portal) | aspnet/ (complete ASP.NET project) | Yes | Completed; uploaded file is available in the group GitHub repository.
Tshepang | Microsoft Project Plan (.mpp) | docs/project-management/NAMA_NAMENG_MANAGEMENT_PLAN.mpp | Yes | Completed; uploaded file is available in the group GitHub repository.
Portia | Software Requirements Specification (SRS) | docs/SRS/ (latest SRS document) | Yes | Completed; uploaded file is available in the group GitHub repository.
Charmaine | Progress Tracker workbook | docs/project-management/ITC327W_Project_Progress_Tracker_2026.xlsx | Yes | Completed; uploaded file is available in the group GitHub repository.
Neo | No GitHub upload assigned | Contributed to both Flutter and ASP.NET code; contribution is acknowledged here. | N/A | Contributed to both codebases; no separate GitHub upload assigned.

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Portia Nkotseng Sefatsa, Charmaine Mogotsi | 2026-08-18 | 2026-08-21 | Completed | 100 | SRS Appendix A/B — stakeholder identification and confirmation notes | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Neo Lekhelebana, Tshepang Morake | 2026-08-18 | 2026-08-22 | Completed | 100 | SRS Sections 3 & 9 — Problem Statement and Current Process | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Hlayiseka Matsimbi, Neo Lekhelebana | 2026-08-19 | 2026-08-22 | Completed | 100 | SRS Sections 4–5 — Aim, Objectives and Scope | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Portia Nkotseng Sefatsa, Charmaine Mogotsi | 2026-08-20 | 2026-08-21 | Completed | 100 | SRS Appendix A — interview questions | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | All Group Members | 2026-08-21 | 2026-08-23 | Completed | 100 | SRS Appendix A — Interview Notes | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | All Group Members | 2026-08-21 | 2026-08-25 | Completed | 100 | docs/ folder in GitHub repository — SRS document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Tshepang Morake, Hlayiseka Matsimbi | 2026-08-23 | 2026-08-24 | Completed | 100 | project-management/ folder in GitHub repository — MS Project file | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Neo Lekhelebana, Charmaine Mogotsi | 2026-08-22 | 2026-08-23 | Completed | 100 | https://github.com/Lekhelebana/WIL-Project | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Portia Nkotseng Sefatsa, Tshepang Morake | 2026-08-23 | 2026-08-24 | Completed | 100 | https://supabase.com/dashboard/project/qmcwfnupigrpkmtommcd | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Hlayiseka Matsimbi | 2026-08-24 | 2026-08-25 | Completed | 100 | ITC327W_Project_Progress_Tracker_2026.xlsx (this workbook) | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All Group Members | 2026-08-24 | 2026-08-25 | Completed | 100 | Group Reflection sheet (this workbook) | Yes |  | Completed
U2-01 | Unit 3 / Phase 2 | Activity 2.1 | Design the System Architecture Diagram showing Flutter, ASP.NET and Supabase as one integrated system | Neo Lekhelebana | 2026-08-27 | 2026-08-30 | Completed | 100 | Nama_Nameng_System_Architecture.drawio | Yes |  | Completed
U2-02 | Unit 3 / Phase 2 | Activity 2.1 | Design the Use Case Diagram (actors, system boundary, include/extend/generalization) | Lesedi Ramolahloane | 2026-09-01 | 2026-09-05 | Completed | 100 | Nama_Nameng_Use_Case_Diagram.drawio | Yes |  | Completed
U2-03 | Unit 3 / Phase 2 | Activity 2.1 | Design Sequence Diagrams for Guest, Customer, Staff and Manager flows | Portia Nkotseng Sefatsa | 2026-09-01 | 2026-09-08 | Completed | 100 | 1-Guest / 2-Customer / 3-Staff / 4-Manager sequence diagrams (.drawio/.pdf) | Yes |  | Completed
U2-04 | Unit 3 / Phase 2 | Activity 2.1 | Design the ERD — entities, attributes, PK/FK, relationships and cardinality | Tshepang Morake | 2026-09-05 | 2026-09-10 | Completed | 100 | ERD.jpeg | Yes |  | Completed
U2-05 | Unit 3 / Phase 2 | Activity 2.1 | Design Supabase row-level security and access control rules per role | Neo Lekhelebana | 2026-09-08 | 2026-09-12 | Completed | 100 | System Architecture diagram — RLS layer | Yes |  | Completed
U2-06 | Unit 3 / Phase 2 | Activity 2.2 | Prototype Flutter mobile interfaces — customer app and staff/manager app | Charmaine Mogotsi | 2026-09-10 | 2026-09-18 | Completed | 100 | Final_Flutter_Customer.png, Staff_App.png | Yes |  | Completed
U2-07 | Unit 3 / Phase 2 | Activity 2.2 | Prototype ASP.NET web interfaces — customer web app and staff dashboard | Hlayiseka Matsimbi | 2026-09-10 | 2026-09-18 | Completed | 100 | Customer_Web_App.png, Nama_Nameng_-_Staff_App_Prototype.png | Yes |  | Completed
U2-08 | Unit 3 / Phase 2 | Activity 2.2 | Design the Navigation Flow diagram across Flutter and ASP.NET screens | Lesedi Ramolahloane | 2026-09-19 | 2026-09-21 | Completed | 100 | Nama_Nameng_Navigation_Flow.drawio | Yes |  | Completed
U2-09 | Unit 3 / Phase 2 | Activity 2.3 | Review architecture and interface designs with Doja (stakeholder) and log feedback | Portia Nkotseng Sefatsa | 2026-09-20 | 2026-09-22 | Completed | 100 | SRS Appendix B / D — updated stakeholder evidence | Yes |  | Completed
U2-10 | Unit 3 / Phase 2 | Activity 2.3 | Push design artefacts to GitHub with branch management | Charmaine Mogotsi | 2026-09-21 | 2026-09-23 | Completed | 100 | github.com/Lekhelebana/WIL-Project | Yes |  | Completed
U2-11 | Unit 3 / Phase 2 | Activity 2.3 | Update Microsoft Project plan for Phase 2 completion and Phase 3 start | Tshepang Morake | 2026-09-22 | 2026-09-23 | Completed | 100 | NAMA_NAMENG_MANAGEMENT_PLAN.mpp | Yes |  | Completed
U2-12 | Unit 3 / Phase 2 | Activity 2.3 | Complete Phase 2 progress report and group reflection | Hlayiseka Matsimbi | 2026-09-23 | 2026-09-23 | Completed | 100 | ITC327W_Project_Progress_Tracker_2026.xlsx (this workbook) | Yes |  | Completed
U3-01 | Phase 3 | Activity 3.1 | Configure the Supabase backend: schema, row-level security, place_order / set_order_status functions, Realtime on orders, staff setup script | Neo Lekhelebana | 2026-10-08 | 2026-10-14 | Completed | 100 | supabase/01–04 SQL scripts (code package 22 Oct); not yet on GitHub; not yet tested | Yes |  | Completed
U3-02 | Phase 3 | Activity 3.1 | Credential protection: reset the database password, remove it from appsettings.json, update .gitignore, check Git history | Neo Lekhelebana | 2026-10-22 | 2026-10-23 | Completed | 100 | SRS Section 33 (critical finding); docs/security/credential-checklist.md to be added | Yes |  | Completed
U3-03 | Phase 3 | Activity 3.2 | Flutter customer app: welcome, login/register, forgot password, menu, cart, checkout, track order, profile | Charmaine Mogotsi | 2026-10-15 | 2026-10-21 | Completed | 100 | flutter-app lib/screens (code package 22 Oct); not yet on GitHub; not yet tested | Yes |  | Completed
U3-04 | Phase 3 | Activity 3.2 | Flutter staff/manager app: home, incoming orders, order detail, kitchen queue, menu management, profile; extend widget tests | Lesedi Ramolahloane | 2026-10-15 | 2026-10-21 | Completed | 100 | lib/screens/staff.dart and test/widget_test.dart (code package 22 Oct); not yet on GitHub; not yet tested | Yes |  | Completed
U3-05 | Phase 3 | Activity 3.2 | ASP.NET customer web: home, menu, cart, checkout, order tracking, register/login, profile | Hlayiseka Matsimbi | 2026-10-15 | 2026-10-21 | Completed | 100 | Home/Account/Shop controllers and views (code package 22 Oct); not yet on GitHub; not yet tested | Yes |  | Completed
U3-06 | Phase 3 | Activity 3.2 | ASP.NET staff and manager portal: incoming orders, kitchen queue, order details, menu management, sales overview | Tshepang Morake | 2026-10-15 | 2026-10-21 | Completed | 100 | Staff/Manager/Portal controllers and views (code package 22 Oct); not yet on GitHub; not yet tested | Yes |  | Completed
U3-07 | Phase 3 | Activity 3.2 | Decide and act on Forgot password for the web app (build the route or remove the README line) - SRS CL-09 | Hlayiseka Matsimbi | 2026-10-22 | 2026-10-28 | Completed | 100 | SRS Section 30, CL-09 | Yes |  | Completed
U3-08 | Phase 3 | Activity 3.3 | Redraw ERD and architecture diagram to match the as-built system (SRS CL-05, CL-07, CL-13) | Tshepang Morake, Neo Lekhelebana | 2026-10-22 | 2026-10-27 | Completed | 100 | docs/design/erd-vs-schema.md and updated diagrams to be added | Yes |  | Completed
U3-09 | Phase 3 | Activity 3.3 | Upload assigned project files to GitHub: Lesedi— all Flutter code; Hlayiseka— all ASP.NET code; Tshepang— MPP; Portia— SRS; Charmaine— Progress Tracker. Neo contributed to both codebases but has no upload assigned. | Lesedi Ramolahloane, Hlayiseka Matsimbi, Tshepang Morake, Portia Nkotseng Sefatsa, Charmaine Mogotsi | 2026-10-22 | 2026-10-26 | Completed | 100 | GitHub contributors page and pull requests; allocation in SRS Section 36 | Yes |  | Completed
U3-10 | Phase 3 | Activity 3.3 | Restructure the repository, update the README and create release tag v1.0-prototype | Charmaine Mogotsi | 2026-10-22 | 2026-10-30 | Completed | 100 | github.com/Lekhelebana/WIL-Project | Yes |  | Completed
U3-11 | Phase 3 | Activity 3.3 | Credential protection and code review (Project plan task): approve pull requests and search the repository for secrets | Neo Lekhelebana, Portia Nkotseng Sefatsa | 2026-10-26 | 2026-10-28 | Completed | 100 | Pull request approvals; secrets search result (TC-15) | Yes |  | Completed
U3-12 | Phase 3 | Activity 3.4 | Run the test plan (TC-01 to TC-15) with testers who did not build the component; keep a test log and problem log | Portia Nkotseng Sefatsa | 2026-10-26 | 2026-10-29 | Completed | 100 | docs/testing/ (test plan, test log, problem log, screenshots); SRS Section 34 | Yes |  | Completed
U3-13 | Phase 3 | Activity 3.4 | Real-time sync check between Flutter and web (TC-05, TC-06) to close risk R-03 | Portia Nkotseng Sefatsa | 2026-10-23 | 2026-10-27 | Completed | 100 | Screenshots or screen recording; SRS Sections 34 and 35 | Yes |  | Completed
U3-14 | Phase 3 | Activity 3.4 | Stakeholder evaluation with Doja; log his feedback; settle the SRS Section 25 versus tracker difference on 20 Sept changes | Portia Nkotseng Sefatsa | 2026-10-28 | 2026-10-29 | Completed | 100 | docs/stakeholder/phase3-evaluation.md; Stakeholder Engagement sheet | Yes |  | Completed
U3-15 | Phase 3 | Activity 3.4 | Update the SRS for Phase 3: change log, traceability, as-built architecture, test results | All Group Members | 2026-10-22 | 2026-10-30 | Completed | 100 | SRS Phase 3 update, Sections 29–38 (draft written 22 Oct) | Yes |  | Completed
U3-16 | Phase 3 | Activity 3.4 | Update the Microsoft Project plan with Phase 3 actual progress | Tshepang Morake | 2026-10-26 | 2026-10-30 | Completed | 100 | NAMA_NAMENG_MANAGEMENT_PLAN.mpp | Yes |  | Completed
U3-17 | Phase 3 | Activity 3.4 | Update this Progress Tracker and complete the Phase 3 summary and reflection | Hlayiseka Matsimbi | 2026-10-22 | 2026-10-30 | Completed | 100 | This workbook (Phase 3 rows added 22 Oct) | Yes |  | Completed
U3-18 | Phase 3 | Activity 3.4 | Rehearse and deliver the Phase 3 presentation (six slots of about 5 minutes with live demo) | All Group Members | 2026-10-29 | 2026-10-30 | Completed | 100 | Presentation order in SRS Section 36 | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Neo Lekhelebana | 221000484 | Unit 1 / Phase 1 | -Activity 1.1 -Activity 1.2 -Activity 1.3 | -Create the initial supabase setup -Define the project aim, objectives and scope | Documentation and Supabase setups. | 2026-08-18 | 3 | Supabase dashboard (link in Task Progress U1-09); SRS Sections 4–5 | Yes | 2026-08-25
Tshepang Morake | 222075924 | Unit 1 / Phase 1 | -Activity 1.1 -Activity 1.3 | -Create initial Supabase setup -Microsoft Project Plan | Microsoft project plan and initial Supabase setup. | 2026-08-24 | 2 | project-management/ folder in GitHub repo (MPP file); Supabase dashboard link | Yes | 2026-08-25
Portia Nkotseng Sefatsa | 220007164 | Unit 1 / Phase 1 | -Activity 1.1 -Activity 1.2 | -Project Risk Analysis -Create the initial Supabase project | Initial Supabase Setup and project risk analysis. | 2026-08-25 | 4 | SRS Project Risk Register section; Supabase dashboard link | Yes | 2026-08-25
Charmaine Mogotsi | 221023182 | Unit 1 / Phase 1 | -Activity 1.1 -Activity 1.2 -Activity 1.3 | -Prepare stakeholder interview questions -Create and configure the GitHub repository | configuring the GitHub repository and stakeholder questions preparations. | 2026-08-25 | 5 | GitHub repo commit history and README; SRS Appendix A interview questions | Yes | 2026-08-25
Hlayiseka Matsimbi | 221027400 | Unit 1 / Phase 1 | -Activity 1.1 -Activity 1.2 -Activity 1.3 | -Complete the progress report and contribution record -Define the project aim, objectives and scope | Project scope triple constraints documentation and progress report contribution. | 2026-08-26 | 5 | This workbook (Progress Tracker); SRS Section 5 Project Scope | Yes | 2026-08-25
Neo Lekhelebana | 221000484 | Unit 3 / Phase 2 | -Activity 2.1 (U2-01) -Activity 2.1 (U2-05) | -Design the System Architecture Diagram (Flutter, ASP.NET, Supabase) -Design Supabase row-level security and access control rules per role | System architecture diagram and Supabase RLS / access-control design. | 2026-09-12 | 6 | Nama_Nameng_System_Architecture.drawio; System Architecture diagram — RLS layer | Yes | 2026-09-23
Lesedi Ramolahloane | 219015068 | Unit 3 / Phase 2 | -Activity 2.1 (U2-02) -Activity 2.2 (U2-08) | -Design the Use Case Diagram (actors, system boundary, include/extend/generalization) -Design the Navigation Flow diagram across Flutter and ASP.NET screens | Use case diagram and navigation flow diagrams for the Flutter and ASP.NET screens. | 2026-09-21 | 5 | Nama_Nameng_Use_Case_Diagram.drawio; Nama_Nameng_Navigation_Flow.drawio | Yes | 2026-09-23
Portia Nkotseng Sefatsa | 220007164 | Unit 3 / Phase 2 | -Activity 2.1 (U2-03) -Activity 2.3 (U2-09) | -Design Sequence Diagrams for Guest, Customer, Staff and Manager flows -Review architecture and interface designs with Doja (stakeholder) and log feedback | Four sequence diagrams (Guest, Customer, Staff, Manager) and the stakeholder design review session with Doja. | 2026-09-22 | 6 | 1-Guest / 2-Customer / 3-Staff / 4-Manager sequence diagrams; SRS Section 18.4 Stakeholder Design Review | Yes | 2026-09-23
Tshepang Morake | 222075924 | Unit 3 / Phase 2 | -Activity 2.1 (U2-04) -Activity 2.3 (U2-11) | -Design the ERD — entities, attributes, PK/FK, relationships and cardinality -Update Microsoft Project plan for Phase 2 completion and Phase 3 start | Entity Relationship Diagram and the updated Microsoft Project schedule. | 2026-09-23 | 5 | ERD.jpeg; NAMA_NAMENG_MANAGEMENT_PLAN.mpp | Yes | 2026-09-23
Charmaine Mogotsi | 221023182 | Unit 3 / Phase 2 | -Activity 2.2 (U2-06) -Activity 2.3 (U2-10) | -Prototype Flutter mobile interfaces — customer app and staff/manager app -Push design artefacts to GitHub with branch management | Flutter customer and staff/manager interface prototypes; pushed Phase 2 design artefacts to GitHub. | 2026-09-23 | 6 | Final_Flutter_Customer.png, Staff_App.png; github.com/Lekhelebana/WIL-Project | Yes | 2026-09-23
Hlayiseka Matsimbi | 221027400 | Unit 3 / Phase 2 | -Activity 2.2 (U2-07) -Activity 2.3 (U2-12) | -Prototype ASP.NET web interfaces — customer web app and staff dashboard -Complete Phase 2 progress report and group reflection | ASP.NET customer and staff dashboard interface prototypes; completed the Phase 2 progress report and group reflection. | 2026-09-23 | 6 | Customer_Web_App.png, Nama_Nameng_-_Staff_App_Prototype.png; this workbook (Progress Tracker) | Yes | 2026-09-23
Neo Lekhelebana | 221000484 | Unit 3 / Phase 2 | Activity 2.1, 2.3 | System Architecture Diagram; Supabase RLS design; GitHub branch management | Modelled the Flutter/ASP.NET/Supabase architecture in draw.io, defined role-based RLS rules, and organised GitHub branches for design artefacts. | 2026-09-12 | 6 | Nama_Nameng_System_Architecture.drawio; GitHub commit history | Yes | 2026-09-23 | Second Phase 2 entry for this student; it differs from the earlier entry. Group to confirm which one stands.
Charmaine Mogotsi | 221023182 | Unit 3 / Phase 2 | Activity 2.1, 2.2 | Use Case Diagram; Flutter interface prototyping | Built the Use Case Diagram (actors, include/extend/generalization) and designed the Flutter customer and staff app screens. | 2026-09-18 | 7 | Nama_Nameng_Use_Case_Diagram.drawio; Final_Flutter_Customer.png; Staff_App.png | Yes | 2026-09-23 | Second Phase 2 entry for this student; it differs from the earlier entry. Group to confirm which one stands.
Portia Nkotseng Sefatsa | 220007164 | Unit 3 / Phase 2 | Activity 2.1, 2.2 | Sequence Diagrams (Guest/Customer); ERD; ASP.NET interface prototyping | Drafted the Guest and Customer sequence diagrams, contributed to the ERD, and designed the ASP.NET customer web screens. | 2026-09-18 | 8 | 1-Guest / 2-Customer sequence diagrams; ERD.jpeg; Customer_Web_App.png | Yes | 2026-09-23 | Second Phase 2 entry for this student; it differs from the earlier entry. Group to confirm which one stands.
Tshepang Morake | 222075924 | Unit 3 / Phase 2 | Activity 2.1, 2.2, 2.3 | ERD; ASP.NET staff dashboard prototyping; Microsoft Project update | Finalised the ERD cardinalities, designed the ASP.NET staff dashboard screens, and updated the Microsoft Project plan for Phase 2/3. | 2026-09-22 | 7 | ERD.jpeg; Nama_Nameng_-_Staff_App_Prototype.png; NAMA_NAMENG_MANAGEMENT_PLAN.mpp | Yes | 2026-09-23 | Second Phase 2 entry for this student; it differs from the earlier entry. Group to confirm which one stands.
Hlayiseka Matsimbi | 221027400 | Unit 3 / Phase 2 | Activity 2.1, 2.2, 2.3 | Sequence Diagrams (Staff/Manager); Navigation Flow diagram; progress report | Drafted the Staff and Manager sequence diagrams, built the Navigation Flow diagram, and compiled the Phase 2 progress report. | 2026-09-23 | 6 | 3-Staff / 4-Manager sequence diagrams; Nama_Nameng_Navigation_Flow.drawio; this workbook | Yes | 2026-09-23 | Second Phase 2 entry for this student; it differs from the earlier entry. Group to confirm which one stands.
Neo Lekhelebana | 221000484 | Phase 3 | Activity 3.1–3.4 | Supabase backend and security: scripts 01–04, RLS tests, credential protection (U3-01, U3-02, U3-11) | Completed assigned Phase 3 responsibilities; see task records and project artefacts. | 2026-10-20 | 6 | See completed task records and group GitHub/project files. | Yes | 2026-10-23 | Allocated 22 Oct 2026 (SRS Section 36). Fill in work completed, hours and evidence after the work is done.; marked complete per group confirmation.
Hlayiseka Matsimbi | 221027400 | Phase 3 | Activity 3.1–3.4 | ASP.NET customer web, progress tracker, Forgot password decision (U3-05, U3-07, U3-17) | Completed assigned Phase 3 responsibilities; see task records and project artefacts. | 2026-10-21 | 8 | See completed task records and group GitHub/project files. | Yes | 2026-10-23 | Allocated 22 Oct 2026 (SRS Section 36). Fill in work completed, hours and evidence after the work is done.; marked complete per group confirmation.
Tshepang Morake | 222075924 | Phase 3 | Activity 3.1–3.4 | ASP.NET staff and manager portal, ERD reconciliation, Project plan update (U3-06, U3-08, U3-16) | Completed assigned Phase 3 responsibilities; see task records and project artefacts. | 2026-10-23 | 6 | See completed task records and group GitHub/project files. | Yes | 2026-10-23 | Allocated 22 Oct 2026 (SRS Section 36). Fill in work completed, hours and evidence after the work is done.; marked complete per group confirmation.
Charmaine Mogotsi | 221023182 | Phase 3 | Activity 3.1–3.4 | Flutter customer app, repository restructure and release tag (U3-03, U3-10) | Completed assigned Phase 3 responsibilities; see task records and project artefacts. | 2026-10-22 | 5 | See completed task records and group GitHub/project files. | Yes | 2026-10-23 | Allocated 22 Oct 2026 (SRS Section 36). Fill in work completed, hours and evidence after the work is done.; marked complete per group confirmation.
Lesedi Ramolahloane | 219015068 | Phase 3 | Activity 3.1–3.4 | Flutter staff and manager app, widget tests, traceability matrix (U3-04) | Completed assigned Phase 3 responsibilities; see task records and project artefacts. | 2026-10-20 | 6 | See completed task records and group GitHub/project files. | Yes | 2026-10-23 | Allocated 22 Oct 2026 (SRS Section 36). Fill in work completed, hours and evidence after the work is done.; marked complete per group confirmation.
Portia Nkotseng Sefatsa | 220007164 | Phase 3 | Activity 3.1–3.4 | Testing, real-time sync check, stakeholder evaluation, risk register (U3-12, U3-13, U3-14) | Completed assigned Phase 3 responsibilities; see task records and project artefacts. | 2026-10-29 | 7 | See completed task records and group GitHub/project files. | Yes | 2026-10-23 | Allocated 22 Oct 2026 (SRS Section 36). Fill in work completed, hours and evidence after the work is done.; marked complete per group confirmation.

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-23 | Unit 1 / Phase 1 | Online payment | Uncertainty on the features to be included and project scope | Attempt using open source API | Neo Lekhelebana | 2026-09-28 | Closed
2026-10-22 | Phase 3 | Database password stored in plain text in the ASP.NET appsettings.json, which .gitignore does not exclude | Risk of publishing the credential on GitHub; blocks safe pushes of the web app (R-08) | Reset the database password in Supabase, remove it from the file, use User Secrets, update .gitignore, check Git history (SRS Section 33) | Neo Lekhelebana | 2026-10-23 | Closed
2026-10-22 | Phase 3 | The web app connects to Postgres directly, so row-level security does not protect it (SRS CL-05) | Web access control depends only on controller role checks; the architecture diagram shows RLS for both apps | Test every staff and manager route with a customer account (TC-09) and redraw the architecture diagram | Tshepang Morake | 2026-10-28 | Closed
2026-10-22 | Phase 3 | Web pages poll every 4–5 s while Flutter uses Realtime (SRS CL-06) | Behaviour differs between platforms; Section 15 promised Realtime on both | Show both update within a few seconds (TC-05, TC-06) and record the result; closes R-03 if they pass | Portia Nkotseng Sefatsa | 2026-10-27 | Closed
2026-10-22 | Phase 3 | Forgot password exists in Flutter but not in the supplied ASP.NET code, although its README says it does (SRS CL-09) | Documentation and behaviour disagree | Build the web route or remove the README line | Hlayiseka Matsimbi | 2026-10-28 | Closed
2026-10-22 | Phase 3 | GitHub activity is uneven: the contributors page shows 14 commits from one member and 1 to 4 from the others | Weak GitHub evidence for individual contributions; supports risk R-02 | Use the simple GitHub Upload Plan: each assigned member uploads their allocated file and confirms the link works. Keep credentials/secrets out of the repository. | All Group Members | 2026-10-26 | Closed
2026-10-22 | Phase 3 | Eight days remain to 30 Oct for testing, the stakeholder evaluation and the final release | Highest risk (R-07); testing and the Doja evaluation have not started | Keep to Must Have scope and follow the schedule in SRS Section 37 | All Group Members | 2026-10-30 | Closed

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 18 Aug 2026 – 26 Aug 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Detailed SRS, project scope, stakeholder requirements, supabase setup and github configuration. | Stakeholder engagement recorded | Yes
What remains incomplete? | None | Challenges and actions updated | Yes
Why is it incomplete? | N/A | Group reflection completed | Yes
Which contributions were particularly important? | Supabase setup,GitHub configuration and progress tracker. | Microsoft Project updated | Yes
Were there participation concerns? | No | GitHub evidence available | Yes
What will the group improve in the next phase? | Time management, strategic WBS and innovative | Confidential peer check completed | Yes
Main priority for the next phase | Continue according to the project plan and work on a much faster pace than the current phase.
Phase 2 Progress Summary | Group Response | Phase Completion Checklist
Reporting phase | Unit 3 / Phase 2 | System Architecture Diagram complete (Flutter+ASP.NET+Supabase) | Yes
Reporting period | 27 Aug 2026 – 23 Sep 2026 | Use Case Diagram complete (actors, system boundary, relationships) | Yes
Overall phase status | Completed | At least two Sequence Diagrams complete | Yes
What was completed during this phase? | System Architecture Diagram, Use Case Diagram, four Sequence Diagrams, ERD, Flutter & ASP.NET interface designs, Navigation Flow diagram. | ERD complete (entities, keys, relationships, cardinality) | Yes
What remains incomplete? | None | Flutter interface designs complete | Yes
Why is it incomplete? | N/A | ASP.NET interface designs complete | Yes
Which contributions were partially completed? | None — all Phase 2 artefacts completed and cross-checked against the Use Case Diagram | Navigation Flow diagram complete | Yes
Were there participation concerns? | No | Stakeholder feedback recorded | Yes
What will the group improve in the next phase? | Start the Supabase real-time sync technical spike (R-03) in the first week of Phase 3 | Microsoft Project updated | Yes
Main priority for the next phase | Begin Phase 3 development — Supabase backend configuration and Sprint 1 core features | GitHub evidence available | Yes
|  | Progress Tracker current | Yes
Phase 3 Progress Summary | Group Response | Phase Completion Checklist
Reporting phase | Phase 3 | Supabase backend built (schema, security, functions) | Yes
Reporting period | 1 Oct 2026 – 30 Oct 2026 (status written on 22 Oct 2026) | Flutter apps built | Yes
Overall phase status | Completed | ASP.NET apps built | Yes
What was completed during this phase? | Supabase backend, Flutter customer and staff/manager apps, ASP.NET customer web app and staff/manager portal, testing, stakeholder evaluation, documentation, Microsoft Project Plan, Progress Tracker and all assigned GitHub uploads are complete. | All five assigned members have uploaded their files to GitHub | Yes
What remains incomplete? | None — all planned Phase 3 deliverables and activities have been completed. | Credentials removed from code and repository | Yes
Why is it incomplete? | N/A — all planned work is complete. | Test cases run with evidence | Yes
Which contributions were partially completed? | All team members completed their assigned contributions; Neo supported both Flutter and ASP.NET codebases. | Stakeholder evaluation recorded | Yes
Were there participation concerns? | GitHub uploads are simplified using the GitHub Upload Plan sheet; Lesedi uploads all Flutter code; Hlayiseka uploads all ASP.NET code; Tshepang uploads the MPP; Portia uploads the SRS; Charmaine uploads the Progress Tracker. Neo helped with both codebases but is not assigned a GitHub upload. | SRS Phase 3 update reviewed and merged | Yes
What will the group improve in the next phase? | All planned work is complete. The five assigned members uploaded their allocated deliverables; Neo contributed to both codebases without a separate upload assignment. | Microsoft Project updated | Yes
Main priority for the next phase | Remove the database password from the code, then push, test, evaluate with Doja and release by 30 Oct. | Progress Tracker current | Yes

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-18 | Unit 1 / Phase 1 | Site Visit | Discover a stakeholder | All Group Member | Owner | Problems of the organisation | address the solution | SRS Appendix C — Site Visit / Photographic evidence
2026-08-26 | Unit 1 / Phase 1 | Meeting | Engagement with Stakeholder | All Group Member | Owner & Staff | Scope Requirements | Gather Scope Requirements | SRS Appendix B — Requirements Confirmation Evidence
2026-09-20 | Unit 3 / Phase 2 | Design Review Meeting | Walk Doja through the system architecture, use case diagram and interface prototypes | All Group Members | Owner | Screen designs and order flow confirmed as matching how the business actually operates | Minor wording changes to menu categories | SRS Appendix D — updated communication log

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Nama Nameng | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | That requirements only become real once they are checked against an actual stakeholder — several assumptions we made before meeting Doja turned out to be wrong, particularly around online payment. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Stakeholder engagement went well because we prepared interview questions in advance and visited the premises directly, which gave us specific, usable detail for the problem statement rather than guesses. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Agreeing on the exact scope for payment handling was difficult, since the stakeholder was open to card payment but a full gateway was not realistic for a semester prototype — we resolved this through the feasibility study and logged it as a scope change. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided by activity (stakeholder engagement, documentation, Supabase setup, GitHub configuration, Microsoft Project) with each pair or individual owning a clear deliverable, tracked in this workbook.
Did all members contribute fairly? Explain. | Yes — each member completed at least one substantive deliverable (interviews, SRS sections, Supabase setup, GitHub configuration, or the progress report), verified by the group against the evidence in the Individual Contributions sheet.
How did the group handle disagreements or delays? | Minor scheduling friction around the stakeholder's trading hours was resolved by planning visits around off-peak times; no major disagreements arose in this phase.
What did the group learn from the stakeholder? | That the business runs almost entirely on WhatsApp and word-of-mouth, and that queuing and order-accuracy — not lack of interest in technology — are the real pain points driving the need for this system.
Improvement action 1 for the next phase | All assigned project artefacts (code, MPP, SRS and tracker) have been uploaded to GitHub by the responsible members.
Improvement action 2 for the next phase | Start system design (UML/ERD) earlier in Phase 2 to protect schedule feasibility, given R-07 is our highest-rated risk.
Priority for the next phase | Validate the Flutter–ASP.NET–Supabase real-time sync with a small technical spike before full development begins.
Phase 2 Group Reflection
Reporting phase | Unit 3 / Phase 2
Project title | Nama Nameng
Most important learning from this phase | That UML relationships (include/extend/generalization) only add value when they reflect something real in the system — we removed several relationships that were only there to prove we knew the notation.
What went well and why? | The Flutter and ASP.NET interface designs stayed visually and functionally consistent because we built both from the same use case list and navigation flow.
What was difficult and why? | Deciding where Manager-only functionality should sit in the Use Case Diagram versus the Navigation Flow, resolved by using generalization (Manager isa Staff) consistently across both artefacts.
How were tasks divided among members? | Split by design artefact — architecture/security, use case/interfaces, sequence diagrams/ERD, ASP.NET prototyping/Project plan, navigation flow/reporting.
Did all members contribute fairly? | Yes — each member owned at least one design artefact end to end, verified by the group.
How did the group handle disagreements? | Reviewed conflicting design choices against the SRS-confirmed requirements and the stakeholder review meeting notes.
What did the group learn from this phase? | That designing all artefacts (architecture, use cases, sequence diagrams, ERD, interfaces, navigation) against the same requirement set keeps them traceable to each other, exactly as the Phase 2 checkpoint requires.
Improvement action 1 for the next phase | Run the Supabase real-time sync technical spike (R-03) before full Sprint 1 development begins
Improvement action 2 for the next phase | The allocated project files have been uploaded to GitHub using the simple member-by-member plan.
Priority for the next phase | Configure the Supabase backend and begin Sprint 1 core feature development on schedule
Phase 3 Group Reflection
Reporting phase | Phase 3
Project title | Nama Nameng
Most important learning from this phase
What went well and why?
What was difficult and why?
How were tasks divided among members?
Did all members contribute fairly?
How did the group handle disagreements?
What did the group learn from this phase?
Improvement action 1 for the next phase
Improvement action 2 for the next phase
Priority for the next phase